## Product-Backlog
Gathering |  |  |  | Velocity: 2.0
Theme | ID | User Story | Acceptance Criteria | Sprint | Status | Points | Estimate | Start Date | End Date
oct | 1021 | As visitor I want to register a user account So I can enter the application | a) Allow user to have their own account | Sprint 1 | Completed | 5.0 | 5 | 2015-09-18 | 2015-09-23
| 1022 | As user I want to login my account So I can | a) Allow user to enter the home page | Sprint 1 | Completed | 2.0 | 5 | 2015-09-23 | 2015-09-28
| 10216 | As user I want to change password So I can enhance my account security | a) User can chage the password and save the changing | Sprint 1 | Completed | 3.0 | 5 | 2015-09-28 | 2015-10-03
| 10219 | As user I want to upload my profile picture So I can | a) User can upload the picture | Sprint 1 | Completed | 13.0 | 5 | 2015-10-03 | 2015-10-08
| 10217 | As user I want to get my password by email if i forget it So I can | a) User can receive the email that contain the reseted password | Sprint 1 | Completed | 8.0 | 5 | 2015-10-08 | 2015-10-13
| 10222 | As a user I want to receive an e-mail to notice me So I can know my register is successful | a) User can receive the email that contain the new password | Sprint 1 | Completed | 8.0 | 5 | 2015-10-13 | 2015-10-18
| 10223 | As a user I want to crop my profile picture in square size So I can show the important part of the photo become my profile picture | a) the profile picture can be uploaded to the server b) The browser can retrieve the user's profile picture c) To confirm the profile picture is 200 x 200 pixels | Sprint 2 | To do | 5.0 | 5 | 2015-10-18 | 2015-10-23
| 10214 | As user I want to invite others be my friends So I can | a) search user by email b) add user to friend list | Sprint 2 | To do | 3.0 | 5 | 2015-10-23 | 2015-10-28
| 10213 | As user I want to see my friend list So I can | a) The users can see the information of their friends | Sprint 2 | To do | 3.0 | 5 | 2015-10-28 | 2015-11-02
| 10224 | As a user I want to show a number to someone who didn't vote in previous activities So I can | a) show the counter in user profile | Sprint 2 | To do | 3.0 | 10 | 2015-11-02 | 2015-11-12
| 10221 | As user I want to edit my friend list So I can | a) User can add and remove friends to the friend list | Sprint 2 | To do | 3.0 | 10 | 2015-11-12 | 2015-11-22
| 1023 | As group owner I want to create a group by providing group name So I can | a) create a group with group name | Sprint 2 | To do | 5.0 | 10 | 2015-11-22 | 2015-12-02
| 1024 | As group owner I want to invite user to join my group So I can | a) search friends from friend list b) add friends to the group | Sprint 3 | To do | 3.0 | 7 | 2015-12-02 | 2015-12-09
| 1025 | As group owner I want to configure the group settings So I can customize the gathering | a) change the group name b) change the activity type c) change the available period | Sprint 3 | To do | 8.0 | 10 | 2015-12-09 | 2015-12-19
| 1026 | As user I want to provide an available date or period So I can | a) set available date to group setting | Sprint 3 | To do | 3.0 | 5 | 2015-12-19 | 2015-12-24
| 10212 | As user I want to see my current activities So I can | a) see the user activities when user login our website | Sprint 3 | To do | 3.0 | 5 | 2015-12-24 | 2015-12-29
| 10218 | As user I want to receive the notification So I can know news of the activities | a) receive an e-mail when new group is created | Sprint 3 | To do | 3.0 | 5 | 2015-12-29 | 2016-01-03
| 1028 | As group owner I want to choose the date if there are more than one choices have the same voting So I can | a) system generate a date from choices | Sprint 3 | To do | 8.0 | 5 | 2016-01-03 | 2016-01-08
| 10225 | As a user I want to count how many times does someone didn't vote So I can | a) add one to counter if the user didn't vote | Sprint 4 | To do | 3.0 | 10 | 2016-01-08 | 2016-01-18
| 1027 | As user I want to suggest some of the gathering details So I can | a) group member can share the suggestions b) suggestion be the choice of voting | Sprint 4 | To do | 8.0 | 10 | 2016-01-18 | 2016-01-28
| 1029 | As user I want to vote the gathering details So I can | a) group member can vote | Sprint 4 | To do | 5.0 | 10 | 2016-01-28 | 2016-02-07
| 10211 | As user I want to see the dashboard So I can | a) count the voting result b) show the result in dashboard | Sprint 4 | To do | 13.0 | 10 | 2016-02-07 | 2016-02-17
| 10210 | As user I want to see the final result So I can | a) show the voting result | Sprint 4 | To do | 5.0 | 10 | 2016-02-17 | 2016-02-27
| 10220 | As user I want to review my past acivities So I can | a) show the past activities in user's home page | Sprint 4 | To do | 3.0 | 10 | 2016-02-27 | 2016-03-08
| Total for theme 'oct' |  |  | 126.0 points / 63.0 days
Total for backlog 'gathering' |  |  |  | 126.0 points / 63.0 days
Formulas:
End Date = [Start Date]+[Estimate]
Start Date = [End Date, row above]

## Sprint1-BurnDownChart
Gathering | [11 empty] | 25 |  | 150
Theme | ID | User Story | Acceptance Criteria | Task | Handler | Sprint | Status | Points | Days | Start Date | End Date | Point | Effort Remaining | Ideal Effort Hours
Oct. | 1021 | As visitor I want to register a user account So I can enter the application | Allow user to have their own account | ● To create the data base to establish a user account ● Create a mail server to send password to user ●Generate a radom password for user | 1,2,3,4,5,6 | Sprint 1 | Completed | 5.0 | 5 | 2015-09-18 | 2015-09-23 | 34 | 130 | 125
| 1022 | As user I want to login my account So I can | Allow user to enter the home page | ●To create the login page ●Create a backend method to authoriz the user | 2,3,4 | Sprint 1 | Completed | 2.0 | 5 | 2015-09-23 | 2015-09-28 | 32 | 120 | 100
| 10216 | As user I want to change password So I can enhance my account security | User can change the password and save the changing | ●To create the page for changing password ●Create a method to update the user account in data base | 1,5,6 | Sprint 1 | Completed | 3.0 | 5 | 2015-09-28 | 2015-10-03 | 29 | 70 | 75
| 10219 | As user I want to upload my profile picture So I can | User can upload the picture | ●To set the seeting page and allow user to upload file ●Create a method to save the base64 file to the file system | 1,2,4 | Sprint 1 | Completed | 13.0 | 5 | 2015-10-03 | 2015-10-08 | 16 | 35 | 50
| 10217 | As user I want to get my password by email if I forget it So I can | User can receive the email that contain the reseted password | ●Generate a radom password for user ●Send the email with the new password by the server. | 1,2,4,6 | Sprint 1 | Completed | 8.0 | 5 | 2015-10-08 | 2015-10-13 | 8 | 15 | 25
| 10222 | As a user I want to receive an e-mail to notice me So I can know my register is successful | User can receive the email that contain the new password | ●Send the email by the server. | 1,2,3,5 | Sprint 1 | Completed | 8.0 | 5 | 2015-10-13 | 2015-10-18 | 0 | 0 | 0
| Total for theme 'Oct.' |  |  | 39.0 points / 13.0 days
1. Ching 2. Carrie 3.Jeffee 4.Sheron 5. Bee 6. Himal
Total for backlog 'gathering' |  |  |  | 39.0 points
Formulas:
End Date = [Start Date]+[Days]
Start Date = [End Date, row above]

## Sprint1-SprintBacklog
Sprint1-Data | [19 empty] | 150 | 1 | 2 | 0 | 2 | 0 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
[21 empty] | 2 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0
[21 empty] | 3 | 0 | 0 | 0 | 2 | 1 | 2 | 0 | 3 | 6 | 6 | 5 | 5 | 5 | 5 | 5 | 5
[21 empty] | 4 | 2 | 1 | 1 | 3 | 1 | 5 | 5 | 5 | 1 | 2 | 2 | 2 | 0 | 2 | 2 | 1
[21 empty] | 5 | 1 | 2 | 0 | 0 | 1 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[21 empty] | 6 | 2 | 0 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 0 | 0 | 1 | 1 | 0
Sprint2-Data | [20 empty] | 1 | 2 | 0 | 2 | 0 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
[21 empty] | 2 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0
[21 empty] | 3 | 0 | 0 | 0 | 2 | 1 | 2 | 0 | 3 | 6 | 6 | 5 | 5 | 5 | 5 | 5 | 5
[21 empty] | 4 | 2 | 1 | 1 | 3 | 1 | 5 | 5 | 5 | 1 | 2 | 2 | 2 | 0 | 2 | 2 | 1
[21 empty] | 5 | 1 | 2 | 0 | 0 | 1 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[21 empty] | 6 | 2 | 0 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 0 | 0 | 1 | 1 | 0
Sprint3-Data | [20 empty] | 1 | 2 | 0 | 2 | 0 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
[21 empty] | 2 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0
[21 empty] | 3 | 0 | 0 | 0 | 2 | 1 | 2 | 0 | 3 | 6 | 6 | 5 | 5 | 5 | 5 | 5 | 5
[21 empty] | 4 | 2 | 1 | 1 | 3 | 1 | 5 | 5 | 5 | 1 | 2 | 2 | 2 | 0 | 2 | 2 | 1
[21 empty] | 5 | 1 | 2 | 0 | 0 | 1 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[21 empty] | 6 | 2 | 0 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 0 | 0 | 1 | 1 | 0
Sprint4-Data | [20 empty] | 1 | 2 | 0 | 2 | 0 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
[21 empty] | 2 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0
[21 empty] | 3 | 0 | 0 | 0 | 2 | 1 | 2 | 0 | 3 | 6 | 6 | 5 | 5 | 5 | 5 | 5 | 5
[21 empty] | 4 | 2 | 1 | 1 | 3 | 1 | 5 | 5 | 5 | 1 | 2 | 2 | 2 | 0 | 2 | 2 | 1
[21 empty] | 5 | 1 | 2 | 0 | 0 | 1 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[21 empty] | 6 | 2 | 0 | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 0 | 0 | 1 | 1 | 0
Gathering
Theme | ID | User Story | Acceptance Criteria | Task | Handler | Ching | Carrie | Jeffee | Sheron | Bee | Himal | Sprint | Status | Points | Days | Start Date | End Date | Point | Effort Remaining | Ideal Effort Hours | Day1-2 | Day3-4 | Day4-5 | Day5-6 | Day7-8 | Day8-9 | Day10-11 | Day12-13 | Day14-15 | Day16-17 | Day18-19 | Day20-21 | Day22-23 | Day24-25 | Day26-27 | Day16 | Day17
Oct. | 1021 | As visitor I want to register a user account So I can enter the application | Allow user to have their own account | ● To create the data base to establish a user account ● Create a mail server to send password to user ●Generate a radom password for user | Ching,Carrie,Jeffee,Sheron,Bee,Himal | 1 | 1 | 1 | 1 | 1 | 1 | Sprint 1 | Completed | 5.0 | 5 | 2015-09-18 | 2015-09-23 | 34 | 130 | 125 | 20 | 18 | 18 | 16 | 16 | 15 | 14 | 13 | 12 | 10 | 8 | 6 | 4 | 2 | 0 | 0 | 0
| 1022 | As user I want to login my account So I can | Allow user to enter the home page | ●To create the login page ●Create a backend method to authoriz the user | Carrie,Jeffee,Sheron, |  | 1 | 1 | 1 |  |  | Sprint 1 | Completed | 2.0 | 5 | 2015-09-23 | 2015-09-28 | 32 | 120 | 100 | 10 | 10 | 10 | 10 | 9 | 8 | 6 | 4 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| 10216 | As user I want to change password So I can enhance my account security | User can change the password and save the changing | ●To create the page for changing password ●Create a method to update the user account in data base | Ching, Bee,Himal | 1 |  |  |  | 1 | 1 | Sprint 1 | Completed | 3.0 | 5 | 2015-09-28 | 2015-10-03 | 29 | 70 | 75 | 50 | 50 | 50 | 50 | 48 | 47 | 45 | 45 | 42 | 36 | 30 | 25 | 20 | 15 | 10 | 5 | 0
| 10219 | As user I want to upload my profile picture So I can | User can upload the picture | ●To set the seeting page and allow user to upload file ●Create a method to save the base64 file to the file system | Ching,Carrie, Sheron, | 1 | 1 |  | 1 |  |  | Sprint 1 | Completed | 13.0 | 5 | 2015-10-03 | 2015-10-08 | 16 | 35 | 50 | 35 | 33 | 32 | 31 | 28 | 27 | 22 | 17 | 12 | 11 | 9 | 7 | 5 | 5 | 3 | 1 | 0
| 10217 | As user I want to get my password by email if I forget it So I can | User can receive the email that contain the reseted password | ●Generate a radom password for user ●Send the email with the new password by the server. | Ching,Carrie, Sheron, Himal | 1 | 1 |  | 1 |  | 1 | Sprint 1 | Completed | 8.0 | 5 | 2015-10-08 | 2015-10-13 | 8 | 15 | 25 | 8 | 7 | 5 | 5 | 5 | 4 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 10222 | As a user I want to receive an e-mail to notice me So I can know my register is successful | User can receive the email that contain the new password | ●Send the email by the server. | Ching,Carrie,Jeffee, Himal | 1 | 1 | 1 |  |  | 1 | Sprint 1 | Completed | 8.0 | 5 | 2015-10-13 | 2015-10-18 | 0 | 0 | 0 | 15 | 13 | 13 | 12 | 11 | 10 | 9 | 7 | 6 | 4 | 3 | 2 | 2 | 2 | 1 | 0 | 0
[12 empty] | Sub-Total | [5 empty] | 39 | 150 | 150
Formulas:
End Date = [Start Date]+[Days]
Start Date = [End Date, row above]