## Backlog Report
gathering | [10 empty] | 25 |  | 150
Theme | ID | User Story | Acceptance Criteria | Comments | Sprint | Status | Points | Days | Start Date | End Date | Point | Effort Remaining | Ideal Effort Hours
Oct. | 1021 | As visitor I want to register a user account So I can enter the application |  |  | Sprint 1 | Completed | 5.0 | 5 | 2015-09-21 | 2015-09-26 | 34 | 130 | 125
| 1022 | As user I want to login my account So I can |  |  | Sprint 1 | Completed | 2.0 | 5 | 2015-09-26 | 2015-10-01 | 32 | 120 | 100
| 1023 | As group owner I want to create a group by providing group name So I can | [5 empty] | 0.0
| 1025 | As group owner I want to configure the group settings So I can customize the gathering | [5 empty] | 0.0
| 1024 | As group owner I want to invite user to join my group So I can | [5 empty] | 0.0
| 1026 | As user I want to provide an available date or period So I can | [5 empty] | 0.0
| 1027 | As user I want to suggest some of the gathering details So I can | [5 empty] | 0.0
| 1028 | As group owner I want to choose the date if there are more than one choices have the same voting So I can | [5 empty] | 0.0
| 1029 | As user I want to vote the gathering details So I can | [5 empty] | 0.0
| 10210 | As user I want to see the final result So I can | [5 empty] | 0.0
| 10211 | As user I want to see the dashboard So I can | [5 empty] | 0.0
| 10212 | As user I want to see my current activities So I can | [5 empty] | 0.0
| 10213 | As user I want to see my friend list So I can | [5 empty] | 0.0
| 10214 | As user I want to invite others be my friends So I can | [5 empty] | 0.0
| 10215 | As user I want to see the others no show count So I can | [5 empty] | 0.0
| 10216 | As user I want to change password So I can enhance my account security |  |  | Sprint 1 | Completed | 3.0 | 5 | 2015-10-01 | 2015-10-06 | 29 | 70 | 75
| 10218 | As user I want to receive the notification So I can know news of the activities | [5 empty] | 0.0
| 10219 | As user I want to upload my profile picture So I can |  |  | Sprint 1 | Completed | 13.0 | 5 | 2015-10-06 | 2015-10-11 | 16 | 35 | 50
| 10220 | As user I want to review my past activities So I can | [5 empty] | 0.0
| 10221 | As user I want to edit my friend list So I can | [5 empty] | 0.0
| 10217 | As user I want to get my password by email if I forget it So I can |  |  | Sprint 1 | Completed | 8.0 | 5 | 2015-10-11 | 2015-10-16 | 8 | 15 | 25
| 10222 | As a user I want to receive an e-mail to notice me So I can know my register is successful |  |  | Sprint 1 | Completed | 8.0 | 5 | 2015-10-16 | 2015-10-21 | 0 | 0 | 0
| Total for theme 'Oct.' |  |  | 39.0 points / 13.0 days
Total for backlog 'gathering' |  |  |  | 39.0 points
Formulas:
End Date = [Start Date]+[Days]
Start Date = [End Date, row above]

## Story List
Theme | ID | User Story | Acceptance Criteria | Comments | Sprint | Status | Points | Days
oct | 1021 | As visitor I want to register a user account So I can enter the application |  |  | Sprint 1 | Completed | 5.0 | 1.7
oct | 1022 | As user I want to login my account So I can |  |  | Sprint 1 | Completed | 2.0 | 0.7
oct | 1023 | As group owner I want to create a group by providing group name So I can | [5 empty] | 0.0
oct | 1025 | As group owner I want to configure the group settings So I can customize the gathering | [5 empty] | 0.0
oct | 1024 | As group owner I want to invite user to join my group So I can | [5 empty] | 0.0
oct | 1026 | As user I want to provide an available date or period So I can | [5 empty] | 0.0
oct | 1027 | As user I want to suggest some of the gathering details So I can | [5 empty] | 0.0
oct | 1028 | As group owner I want to choose the date if there are more than one choices have the same voting So I can | [5 empty] | 0.0
oct | 1029 | As user I want to vote the gathering details So I can | [5 empty] | 0.0
oct | 10210 | As user I want to see the final result So I can | [5 empty] | 0.0
oct | 10211 | As user I want to see the dashboard So I can | [5 empty] | 0.0
oct | 10212 | As user I want to see my current activities So I can | [5 empty] | 0.0
oct | 10213 | As user I want to see my friend list So I can | [5 empty] | 0.0
oct | 10214 | As user I want to invite others be my friends So I can | [5 empty] | 0.0
oct | 10215 | As user I want to see the others no show count So I can | [5 empty] | 0.0
oct | 10216 | As user I want to change password So I can enhance my account security |  |  | Sprint 1 | Completed | 3.0 | 1.0
oct | 10218 | As user I want to receive the notification So I can know news of the activities | [5 empty] | 0.0
oct | 10219 | As user I want to upload my profile picture So I can |  |  | Sprint 1 | Completed | 13.0 | 4.3
oct | 10220 | As user I want to review my past acivities So I can | [5 empty] | 0.0
oct | 10221 | As user I want to edit my friend list So I can | [5 empty] | 0.0
oct | 10217 | As user I want to get my password by email if i forget it So I can |  |  | Sprint 1 | Completed | 8.0 | 2.7
oct | 10222 | As a user I want to receive an e-mail to notice me So I can know my register is successful |  |  | Sprint 1 | Completed | 8.0 | 2.7